## Sheet1
Work Tasks | Planned start | Actual start | Planned complete | Effort allocated
1.1 Mendindentifikasi keperluan sistem
Bertemu dengan customer | Week1, d1 | Week1, d1 | Week1, d1 | 1 pd
mengidentifikasi masalah dan batasan projek | Week1, d2 | Week1, d2 | Week1, d2 | 1 pd
Produk statement | Week1, d3 | Week1, d3 | Week1, d3 | 1 pd
milestone produk statement | Week1, d3 | Week1, d3 | Week1, d3
1.2 Output/Control/Input(OCI)
Membuat fitur-fitur website | Week1, d4 | Week1, d4 |  | 14 pd
Membuat database | week3, d4 | week3, d4 |  | 1 pd
Dokumen OCI | week3, d6 | week3, d6 |  | 4 pd
Review OCI dengan customer | week4, d1 | week4, d1 |  | 4 pd
Melakukan revisi jika perlu | week4, d2 | week4, d2 |  | 5 pd